## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team testing
Stories | Acceptance Criteria | Pass/Fail
Create a New Product (8) | GIVEN I submit a product object WHEN no product with the given name exists THEN the system should create the product, add it to the inventory, save to the persistent store, and return the product object and a status code of 201 | Pass
| GIVEN I submit a product object WHEN a product with the given name already exists THEN the system should return a status code of 409 (CONFLICT) | Pass
Delete a single product(3) | Given I submit a product delete request when the product is successfully deleted and does not show in the inventory then the system should return a status code of 200 (OK). | Pass
| Given I submit a product delete request when the product is not deleted and is still in the inventory then the system should return a status code of 409 (CONFLICT). | Pass
Get Entire Inventory | GIVEN I submit a request for the inventory WHEN products exist in the inventory THEN the system should return a list of products and a status code of 200 (OK) | Pass
| GIVEN I submit a request for the inventory WHEN no products exist in the inventory THEN the system should return an empty list of products and a status code of 200 (OK) | Pass
Update a product | GIVEN I submit a request for the inventory WHEN products exist in the inventory THEN the system should return a list of products and a status code of 200 (OK) | Pass
| GIVEN I submit a request for the inventory WHEN no products exist in the inventory THEN the system should return an empty list of products and a status code of 200 (OK) | Pass
Search for a product | Given that an item is in the inventory I want to be able to find it when I give the search a certain string. | Pass
Get a single product | Given I'm an admin when I submit a request for an item then I should get the item information and a status code of 200 (OK). Otherwise, return a status code of 409(CONFLICT) | Pass
SPRINT 2
Customer Login | Given I am a customer that wants to login WHEN I click login THEN I get taken to a customer page
| GIVEN I enter a username that isn't created WHEN I click the login button, THEN I am given an error that the user is not created | Bug
Inventory Additon | Given I get a new item/run out of an item when I click the + then I add a product to stock | Pass
Inventory Removal | Given I get a new item/run out of an item when I click the x then I delete a product to stock | Bug
Admin Login | Given I want to remove/add a product for purchase WHEN I click the X/+ button THEN item gets removed/added from inventory | Pass
Sprint 3
Shopping Cart | Given that a User submits a request to add an item to the cart, WHEN the user clicks the "add to cart" button, THEN the item gets added to their cart
SignUp Page | Given that a User does not already have login information, WHEN the user clicks the "New User?", THEN the user is taken to a signup page

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a buyer I want to see a list of products so that I choose what to purchase. | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page.
Given that I am not on the Products page when I choose the Products page then I am taken to the Products page.
Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available.
Given that I am on the products page when there are products in the inventory then I see each product and short description.
Given that I am on the products page when there are products in the inventory then I see a means to add each product to my shopping cart.